### Tool: Data Bootcamp Project Plan – accelerated 4 month timeline

| Week | Timeline |
| --- | --- |
| Preparation |  |
| 1 | Identify project members (HQ and FI level) |
| 1-2 | Identify participating FIs Confirm interest and availability |
| 1-2 | Send “Save the date” for all planned meetings and request screening information from participating FIs |
| 3-4 | Analyze FI screening information and decide if crate FI clusters |
| 3-4 | Decide key project parameters: choice of communications platform, rules of engagement, HQ project team member roles |
| 3-4 | HQ project team members get familiar with Data Bootcamp materials |
| Kick-off |  |
| 5 | Articulate the “WHY” for the funder: importance of data analysis and business intelligence work Trust building exercises Align expectations between HQ and portfolio companies Identify pre-emptively issues that may derail the project progress |
| Session 1: Segmentation |  |
| 6 | Agenda: Walk through the dashboards; Define digital vs non digital customers Homework 1: Produce definition of digital and traditional customers; Prepare query that separates digital vs traditional customers; Put output in temporary table/ Excel extract. If unable to complete the work, provide detailed feedback and questions. |
| 7 | Participants work on Homework Support session: Funder HQ provides support to Data Bootcamp participants as needed |
| Session 2: Query |  |
| 8 | Agenda: Review Homework 1 submissions; Walk through query preparation for the 5 dashboards Homework 2: Produce output table for each dashboard |
| 9 | Participants work on Homework Support session: Funder HQ provides support to Data Bootcamp participants as needed |
| Session 3: Visualization |  |
| 10 | Agenda: Review Homework 2 submissions; Prepare visualization using charts and graphs Homework 3: Produce final draft dashboards |
| 11 | Participants work on Homework Support session: Funder HQ provides support to Data Bootcamp participants as needed |
| Session 4: Communication and publishing |  |
| 12 | Agenda: Review Homework 3 submissions; Prepare to get feedback on the dashboards from the business teams and senior management Homework 4: Get confirmation from key stakeholders that visualization is directionally accurate; Finalize dashboards |
| 13 | Participants work on Homework Support session: Funder HQ provides support to Data Bootcamp participants as needed |
| Session 5: Analysis |  |
| 14 | Agenda: Review Homework 4; Analyze dashboards: how do dashboards support decision making? |
| 15 | Participants work on Homework Support session: Funder HQ provides support to Data Bootcamp participants as needed |
| Wrap-up and next steps |  |
| 16 | Feedback from the Data Bootcamp Next steps to continue to build business intelligence capabilities within at HQ and portfolio level |